## Project Planner
Smart Planner-Project Schedule(2017)
[8 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY |  |  | START | DURATION( X 2 ) days
| Start Date | End Date | time axis 2017-02-04 to 2017-05-25
| Start Date | End Date | time axis 2017-02-04 to 2017-05-25
Project Approval
Defining problem domain | 2017-02-04 | 2017-02-07 | 1 | 2
- Understand system operations | 2017-02-04 | 2017-02-05 | 1 | 1
- Understand system requirements | 2017-02-06 | 2017-02-07 | 2 | 1
- Define the scope of the project | 2017-02-06 | 2017-02-07 | 2 | 1
Finalize project proposal | 2017-02-06 | 2017-02-09 | 2 | 2
Project Planning
Feasibility Report | 2017-02-10 | 2017-02-17 | 4 | 4
- Analyze requirements | 2017-02-10 | 2017-02-11 | 4 | 1
- Identify technologies and development environment | 2017-02-12 | 2017-02-13 | 5 | 1
- Risk anaysis | 2017-02-14 | 2017-02-15 | 6 | 1
- Finalize feasibilty report | 2017-02-14 | 2017-02-17 | 6 | 2
Project Schedule | 2017-02-18 | 2017-02-25 | 8 | 4
- Identify milestones and deliverables | 2017-02-18 | 2017-02-19 | 8 | 1
- Identifty dependencies | 2017-02-20 | 2017-02-21 | 9 | 1
- Estimate efforts | 2017-02-20 | 2017-02-23 | 9 | 2
- Generate project schedule | 2017-02-24 | 2017-02-25 | 11 | 1
Project Designing
System Requirement Specification | 2017-02-26 | 2017-03-17 | 12 | 10 | bar: 2017-02-26 to 2017-03-16
- Identify functional/non-functional requirements | 2017-02-26 | 2017-03-03 | 12 | 3
- Prioritize requirements | 2017-03-04 | 2017-03-05 | 15 | 1
- Use case generation | 2017-03-06 | 2017-03-07 | 16 | 1
- Generate SRS document | 2017-03-08 | 2017-03-09 | 17 | 1
System Architecture and Design | 2017-03-10 | 2017-03-17 | 18 | 4
- Identify components of the system | 2017-03-10 | 2017-03-11 | 18 | 1
- Define component and object interactions | 2017-03-12 | 2017-03-15 | 19 | 2
- Generate architeral design | 2017-03-16 | 2017-03-17 | 21 | 1
Progress Report I | 2017-03-08 | 2017-03-09 | 17 | 1
Project Development
Design and implement the database | 2017-03-10 | 2017-03-15 | 18 | 3
- Identify entities and relations | 2017-03-10 | 2017-03-11 | 18 | 1
- Desgin and create database | 2017-03-12 | 2017-03-15 | 19 | 2
Iteration 1 - Implementing Android Application(I) | 2017-03-16 | 2017-03-27 | 21 | 6
- Implemet domain classes | 2017-03-16 | 2017-03-17 | 21 | 1
- Design and create user interfaces | 2017-03-16 | 2017-03-17 | 21 | 1
- Implement time based task scheduling functionality | 2017-03-18 | 2017-03-25 | 22 | 4
- Testing and validation | 2017-03-22 | 2017-03-27 | 24 | 3
Mid Evaluation | 2017-03-28 | 2017-03-31 | 27 | 2
Iteration 2 - Implementing Android Application(II) | 2017-04-01 | 2017-04-12 | 29 | 6
- Implement Location based scheduling functionality | 2017-04-01 | 2017-04-08 | 29 | 4
- Testing and validation | 2017-04-09 | 2017-04-12 | 33 | 2
Progress Report II | 2017-04-13 | 2017-04-14 | 35 | 1
Iteration 3 - Implementing web server | 2017-04-15 | 2017-04-28 | 36 | 7
- Implement domain classes | 2017-04-15 | 2017-04-16 | 36 | 1
- Implement daily report generation functionality | 2017-04-17 | 2017-04-20 | 37 | 2
- Implement Big data analysis functionality | 2017-04-21 | 2017-04-24 | 39 | 2
- Testing and validation | 2017-04-25 | 2017-04-28 | 41 | 2
Testing
Design test plan | 2017-03-12 | 2017-03-15 | 19 | 2
Unit testing | 2017-03-16 | 2017-04-28 | 21 | 22
System testing | 2017-04-29 | 2017-05-04 | 43 | 3
Deployment | 2017-05-05 | 2017-05-06 | 46 | 1
Final Project Report | 2017-05-07 | 2017-05-12 | 47 | 3
Final Evaluation | 2017-05-15 | 2017-05-19 | 51 | 3
Final Paper | 2017-05-21 | 2017-05-26 | 54 | 3